## Sheet1
S.NO | TEAM MEMBER | WORK DESCRIPTION | DATE
1 | ARAVIND, SETHU, SATHISH & NAVEEN | PROJECT STUDY AND DISCUSSION | 2016-11-23
2 | ARAVIND, SETHU, SATHISH & NAVEEN | PROJECT INITIAL CODING DESIGN | 2016-11-24
3 | NAVEEN | STAGES IMPLEMENTATION | 2016-11-25
4 | NAVEEN | INT ALU IMPLEMENTATION | 2016-11-26
5 | ARAVIND | BRANCHING IMPLEMENTATION AND CHANGE | 2016-11-28
6 | SETHU | FORWARDING IMPLEMENTATION | 2016-11-30
7 | ARAVIND | ROB IMPLEMENTATION | 2016-12-03
8 | SATHISH | IQ IMPLEMENTATION | 2016-12-04
9 | ARAVIND | REGISTER RENAMING IMPLEMENTATION | 2016-12-04
10 | SETHU | MULTIPLICATION FU IMPLEMENTATION | 2016-12-05
11 | SATHISH | LOAD/STORE FU IMPLEMENTATION | 2016-12-07
12 | SATHISH | ROB COMMIT IMPLEMENTATION | 2016-12-08
13 | NAVEEN | DISPLAY REGISTER IMPLEMENTATION | 2016-12-10
14 | SETHU | TESTING | 2016-12-11
15 | SATHISH | PROJECT DESIGN DOCUMENT | 2016-12-12
16 | SETHU | TEST CASES AND LOG FILE | 2016-12-12